## Campaign Manager
Rank | Jira | Type | Description | Points
Current Sprint (Sprint T - starts 10/1) - 84pts
1 | 6205 | Bug | & in Campaign Manager search (returning non-& results) | 5
2 | 6454 | Spike | Campaign Manager network permissions permutations | 8
3 |  | TT (group) | CAAS Code Decoupling | 31
| 6398 | Tech Task | Test Data consistency | 13
| 6378 | Tech Task | Media Asset Persistence | 5
| 6379 | Tech Task | Campaign Persistence | 5
| 6380 | Tech Task | Campaign Item Persistence | 8
| 6436 | Epic | Campaign Manager Support for Network User access
4 | 6386 | MMF | Permissions settings for Network User access | 13
| 6391 | Story | Crowd support for Network Users - C/R/U/D permissions assigned at the Network level | 13
5 | 6438 | MMF | Read Permissions for Network Users enforced | 24
| 6389 | Story | Read permissions for Campaigns enforced | 8
| 6439 | Story | Read permissions for Line Items enforced | 13
| 6390 | Story | Read permissions for Ad Assets enforced | 3
6 | 6448 | MMF | Additional permissions enforcement | 3
| 6393 | Story | Ad Assets are always Read-Only for Network Users | 3
Next 2 Sprints (3-6 Weeks)
7 |  | TT | Incoropriate require.js | 21
| 6436 | Epic | Campaign Manager Support for Network User access
8 | 6386 | MMF | Permissions settings for Network User access | 1
| 6437 | Story | Ops Super-User support | 1
9 | 6440 | MMF | Update Permissions for Network Users enforced | 34
| 6441 | Story | Update permissions for Campaigns enforced | 13
| 6442 | Story | Update permissions for Line Items enforced | 21
10 | 6443 | MMF | Create Permissions for Network Users enforced | 21
| 6444 | Story | Create permissions for Campaigns enforced | 8
| 6445 | Story | Create permissions for Line Items enforced | 13
11 | 6446 | MMF | Deactivate Permissions for Network Users enforced | 8
| 6447 | Story | Deactivate permissions for Campaigns enforced | 8
12 | 6448 | MMF | Additional permissions enforcement | 16
| 6410 | Story | Admin only features hidden in GUI for Network Users | 13
| 6452 | Story | Campaign details header information for Network Users | 3
| 6460 | Story | Validate user configuration upon login | 8 | NEW 10/2
13 | 6397 | Tech Task | Performance testing | 13
(7-11 weeks)
14 | 6126 | MMF | Programmer PCC
| 6127 | Story | Enable Programmer Specific Product Category List | 8
| 6128 | Story | Programmer Specific Product Category List - Aliases | 8
| 6129 | Story | Programmer Specific Product Category List - Display | 13
15 | 6202 | MMF | GUI Updates
| 6011 | Story | Campaign Manager GUI Updates - Remove Flight Window | 13
| 6254 | Story | Selecting ASAP Warns User | 3
| 6279 | Story | Break Limit - Warn User | 3
| 6396 | Story | Advanced Search - Description and Label
| 6411 | Story | GUI for Warnings for Line Item License Window
16 | 5574 | MMF | Metadata Targeting Rules
| 5573 | Story | Metadata Targeting Validation Rules - Starts With & Does Not Start With | 8
| 5575 | Story | Metadata Targeting Validation Rules - Is & Is Not | 8
| 5576 | Story | Metadata Targeting Validation Rules - Episode Name | 8
17 | 6010 | MMF | Campaign Manager GUI Updates - Attribute Reductions
| 6012 | Story | Campaign Manager GUI Updates - Goal Type | 13
| 6044 | Story | Campaign Manager GUI Updates - Type | 3
18 | 6048 | MMF | Campaign Manager Improvements - Programmer Release
Need 2/1 | 6003 | Story | Update Privacy Policy | 5
Need 2/1 | 6049 | Story | Update 'Contact Us' Link | 1
| 6000 | Story | Campaign Line Item Update - Value | 2
| 5531 | Story | CM clearly indicates when 1 or more ad assets capable of placing for a provider have been assigned | 13
| 6306 | Story | Add Ad Asset Sort Order | 8
| 6317 |  | Spike to investigate optimistic locking consequences. Use case - two users logged into the same campaign | 8
Need 2/1 | 6195 | Story | Create Link to User Guide | 3
Need 2/1 | 6196 | Story | Create Splash Screen for Downtime | Charley Item
| 6005 | Story | Grid View - Column Headers | 13 Spike
Need 2/1 | 6395 | Story | Default the Network dropdown to a "blank" entry
Include Ad Asset ID in grid
Low | 6034 | Bug | CM: In certain instances, cannot view MSO ad status details from campaign line pop up | 8
Low | 5449 | Bug | Campaign Manager - Thick border lines in Search Results
Low | 5640 | Bug | Add character length validation on campaign description field | 3
Low | 5783 | Bug | Camapign Manager user should not be able to select additional break/position targeting once "Any/Any" has been selected | 5
Low | 5945 | Bug | Goal Quantity Won't Automatically Refresh When Saved on Campaign Grid View | 5
Low | 5954 | Bug | CM. Campaign L-Item Goal Allocation Override Requires Manual Refresh | 13
Low | 5955 | Bug | CM. Changing Campaign Status Updates Order Reference to 'null' | 3
Low | 5953 | Bug | CM: Line Item Metadata Targeting. Numbering Does Not Match | 2
| 6271 | Bug | CM. CAMPAIGN>SHOW Page Can Be Obfuscated
| 6272 | Bug | CM. Line Item Edit. Use of [Enter] Goes to Previous tab
Road Map (12-24 Weeks)
| 5411 | MMF | Creating Campaigns & Line Items that are incolmplete
| 5385 | MMF | Campaign Manager User Metrics
| 5182 | MMF | Basic/Existing Functionality for New Layout
| 3934 | MMF | Campaign Flight Window Rules and Logic
Strategy (24+ Weeks)
User can be assigned Networks from different Programmers
Ad Asset Availability - Cannot differentiate between 'not checked' and 'missing'
Tagging system
User permissions story to be able use programmer at the line item. Be able to log in to see campaigns across programmers
Date picker widget - third option to select start & end date in 1 widget. Ref SPG.com
Remove sliders - replace with text box
Line Item. Network/Ads tab (Multi-providers branch). When only 1 network is listed, it does NOT select it by default (as per Jira 5529)
Line Item. Admin tab. Discount calendar does not permit keyboard entry (but you can click to get a date)
Enhancement. Search UI Improvements
|  |  | Clear all Search conditions after select [Cancel] | Confirm with Ops
|  |  | b. Place the current search conditions in the Breadcrumb Bar | Confirm with Ops
Enhancement. Admin tab. Billing. The Discount End field should default to the same month selected
|  |  | Enhancement. Campaign/LineItem form. Add a “Do You Want To Save Changes” msg when a user moves to another CM page before a change is saved. | Confirm with Ops
|  |  | Enhancement. Campaign Search. Advanced. Ad Asset field. Split it into 1) Media Asset ID, 2)Asset IDstring, ISCI, and 4) Ad-ID | Confirm with Ops
Enhancement. Campaign/Ad Search pages. The borders are either very small or not visible. This gives the impression that there is more data beyond what's displayed in the browser. We would prefer a change that shows definitive ends of the search pages.
Enhancement. Campaign Search. Currently, the grid sorts alphabetically by Campaign Name.
i. Problem. It sorts by 1, 11, 12…..19, not 1,2,3,4
ii. Add the ability to sort by any column.
We had talked about this before. About how the Campaign Show Page kinda looks a little bit bleh, with the way the text is justified. Can we get a story to update that view to get everything left justified and prettied up. I’ll let you word it a little more eloquently
3/24/2014 – Priority or Value not displayed on current CM – should this be displayed?
User can customize which columns are displayed in the Grid View
Ability to create Line Items from grid view
Mass/Bulk Edit from the Grid View
Wish List/Requests
3/24/2014 – Priority or Value not displayed on current CM – should this be displayed?
Ability to sort & filter columns in grid view
Ability to add an ad to many Line Items quickly - find and replace ads en masse
Ability to activate a Line Item immediately after creating Line Item
Functional Breadcrumbs in GUI
‘Alerts’ for user at login – need to discuss this further and define what they should be alerted on
Create Ad Asset when creating Line Item
Dashboards in CM
Ability to make multiple copies of a line item – ability to produce 10 of the same line items instead of just 1 at a time
Should user be able to add an ad to the same line item more than 1x?
Sidebar function similar to OSX
Auto Complete Campaigns that are finished – possible ‘Alert’ system.